## Sheet1
Activity | Time taken (weeks) | Week
Collect requirements | 3 | 0 | 3
Analyze processes | 2 | 3 | 5
Analyze data | 2 | 5 | 7
Design process | 6 | 5 | 11
Design data | 3 | 7 | 10
Design screens | 2 | 11 | 13
Design reports | 4 | 11 | 15
Program | 5 | 15 | 20
Test and Document | 7 | 15 | 22
Install | 2 | 22 | 24